## Instructions
ITC327W Phase 3 Project Progress Tracker
Use this workbook during Phase 3: System Development, Implementation and Final Demonstration. Update it throughout the phase and submit the same workbook with Assessment 3.
Sheet | Purpose | What must be kept current
Project Overview | Group details and automatic development summary | Project details, GitHub link and current Phase 3 progress
Development Progress | Track implementation work | Supabase, Flutter, ASP.NET, integration, SRS, GitHub, Microsoft Project and demonstration preparation
Individual Contributions | Record work personally completed by each student | Activity, responsibility, completed work and evidence
Integration Progress | Track important shared processes across the system | Flutter action, ASP.NET action, shared Supabase information and current working status
Implementation Evidence | Record evidence of the working prototype | Screenshots, recordings, GitHub commits/links and relevant SRS sections
Challenges & Actions | Record development/integration challenges and corrective action | Problem, effect, action, owner, target date and status
Phase Summary | Summarise Phase 3 progress | Completed work, limitations, participation and final readiness
Group Reflection | One shared final group reflection | Development experience, collaboration, challenges and lessons learned
Important
Phase 3 does not require a formal test plan, test cases or defect log. Record normal development checks, working functions, integration progress, challenges and corrections as part of implementation. Do not include passwords, API keys or confidential stakeholder/user information.

## Project Overview
Phase 3 Project Overview
Group |  | Phase 3 Development Summary
Project Title |  | Total tracked items | 13
Stakeholder / Organisation |  | Completed | 0
Group Leader |  | In Progress | 0
Number of Group Members |  | Blocked | 0
GitHub Repository Link |  | Average completion | 0%
Reporting Period
Overall Phase Status | Not Started | Phase 3 Reminder
Phase 3 focuses on implementing and demonstrating the integrated prototype. Track the shared Supabase backend, Flutter mobile application, ASP.NET web application, important shared processes, GitHub evidence, Microsoft Project and the final demonstration.

## Development Progress
Phase 3 Development Progress
Task ID | Development Area | Task / Function | Responsible Student(s) | Planned Date | Actual Completion Date | Status | % Complete | Evidence / GitHub Link | Notes / Action Required
P3-01 | Supabase Backend | Required tables, fields, keys and relationships implemented |  |  | Not Started | 0
P3-02 | Supabase Backend | Authentication and access configured where required |  |  | Not Started | 0
P3-03 | Flutter | Approved mobile screens and navigation implemented |  |  | Not Started | 0
P3-04 | Flutter | Main mobile functions connected to Supabase |  |  | Not Started | 0
P3-05 | ASP.NET | Approved web pages and navigation implemented |  |  | Not Started | 0
P3-06 | ASP.NET | Main web functions connected to Supabase |  |  | Not Started | 0
P3-07 | Integration | Shared Process 1 working across the integrated system |  |  | Not Started | 0
P3-08 | Integration | Shared Process 2 working across the integrated system |  |  | Not Started | 0
P3-09 | Integration | Data fields and status values consistent across applications |  |  | Not Started | 0
P3-10 | SRS | Implementation status, approved changes and known limitations updated |  |  | Not Started | 0
P3-11 | Microsoft Project | Schedule updated to reflect actual development progress |  |  | Not Started | 0
P3-12 | GitHub | Current source code, README and relevant documentation organised |  |  | Not Started | 0
P3-13 | Final Demonstration | Prototype and demonstration flow prepared for panel |  |  | Not Started | 0

## Individual Contributions
Phase 3 Individual Contributions
Student Name | Student Number | Development Area | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / GitHub Link | Verified by Group | Verification Date | Quality / Review Notes | Contribution Status
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started

## Integration Progress
Phase 3 Shared Process and Integration Progress
Shared Process | Related Requirement / Use Case | Flutter Action | ASP.NET Action | Shared Supabase Information | Current Status | Responsible Student(s) | Evidence / Link | Notes / Limitation
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started

## Implementation Evidence
Phase 3 Implementation Evidence
Evidence ID | Application / Area | Function / Feature | Evidence Type | Evidence / Link / File | Related SRS Requirement | Responsible Student | Notes

## Challenges & Actions
Phase 3 Challenges and Corrective Actions
Date Identified | Development / Integration Challenge | Effect on Progress or Function | Action Taken / Required | Responsible Student | Target Date | Status | Resolved Date | Notes / Known Limitation
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started

## Phase Summary
Phase 3 Progress Summary
Reporting Period | Phase 3 Completion Checklist | Complete?
Overall Phase Status | Shared Supabase backend implemented | No
What was completed during Phase 3? | Main Flutter functions working | No
Which functions or processes remain incomplete? | Main ASP.NET functions working | No
What known limitations remain? | At least two shared processes working | No
Which contributions were particularly important? | Integration progress recorded | No
Were there participation concerns? | Implementation evidence recorded | No
Is the prototype ready for the final demonstration? | SRS updated | No
Main priority before final presentation | Microsoft Project updated | No
| GitHub current | No
| Individual contributions recorded | No
| Challenges/actions updated | No
| Known limitations recorded | No
| Group reflection completed | No
| Final demonstration prepared | No

## Group Reflection
Phase 3 Group Reflection
1. What did the group complete successfully during development and implementation?
2. Which development or integration challenges were the most difficult, and how were they addressed?
3. How did the group ensure that Flutter and ASP.NET worked with the same Supabase backend?
4. How was development work divided among group members, and was participation balanced?
5. Which parts of the prototype are strongest, and which limitations remain?
6. What did the group learn from developing and integrating the prototype?
7. What would the group improve if the project continued beyond the final assessment?