## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information |  | Task Status | Count
Group name or number | Group Y (The Zealots) | Completed | 46
Project title | Spanner - Workshop Booking, Stock & Invoicing System | In Progress | 6
Stakeholder or organisation | Riese Auto-Clinic - Michael Riese (Owner/Head Mechanic) | Not Started | 5
Group mentor | Ms Mbele (module mentor, ITC327W) | Delayed | 0
Reporting phase | Unit 3 / Phase 2 (submitted 14 Oct, presented 16 Oct; feedback being applied) | Blocked | 0
Reporting period | Unit 3 / Phase 2 - 16 September to 16 October 2026 (submitted late on 14 Oct, presentation 16 Oct); feedback work 16-23 October | Overdue | 0
Overall status | Phase 2 submitted (one day late) and presented; presentation feedback being applied
Overall % complete | 81% of tracked tasks completed (46 of 57); Microsoft Project shows 81% of the whole plan, including the post-presentation feedback tasks | Contribution Summary | Count
Main achievement | Phase 2 design complete and presented on 16 Oct: architecture, use case and sequence diagrams, ERD, navigation flow, Flutter and ASP.NET designs, all in one public draw.io file; both apps working on one Supabase database; on 16 Oct the feedback was applied the same day (ERD, use cases, sequences, Send on WhatsApp in the web app, Google guide). | Contribution entries | 12
Main challenge | The Phase 2 submission was one day late (due 13 Oct, submitted 14 Oct after Ms Mbele reopened it), and the schedule showed the presentation on the wrong day. Both are now recorded and corrected (U3-38, U3-46). | Verified entries | 12
Next planned activity | Send the corrected schedule and this tracker to Ms Mbele; Gary runs migration 0010 and adds the WhatsApp button to the app; Michael sets up the Google Business Profile; SRS v2.3. | Unverified entries | 0
|  | Stakeholder engagements | 5

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student(s) | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | Gary, Khumo |  |  | Completed | 100 | Stakeholder confirmed: Michael Riese, Owner/Head Mechanic, Riese Auto-Clinic; fully written up in the final SRS Section 1.2, including the directly and indirectly affected users breakdown. | No
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | Gary, Khumo |  |  | Completed | 100 | Current process fully documented in the final SRS Section 1.2 (verbal booking, diagnostics, parts sourcing, repair, invoicing). | No
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | Gary, Khumo |  |  | Completed | 100 | Aim, objectives and initial scope finalised in SRS Sections 1.4-1.5, with the working title "Spanner" and the refined scope carried through to Section 1.11. | No
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | Gary, Khumo |  |  | Completed | 100 | 5-question stakeholder interview prepared and conducted (Activity 1.2) | No
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | Gary, Khumo |  |  | Completed | 100 | Interview conducted with Michael Riese - full Q&A transcript documented in group doc and SRS Section 1.6; signed confirmation letter collected (CUT Department of Information Technology WIL authorisation letter, countersigned by Michael Riese) and included as SRS Appendix E. | No
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | Denny (Mathye MD), Wisani |  |  | Completed | 100 | Final consolidated SRS, Feasibility Study and Risk Register compiled by Wisani and Denny jointly, then revised per Ms Mbele's consultation feedback and again to add the GitHub repository link, an Appendices section, and the vehicle reference image lookup feature (FR-13); Spanner_ITC327W_Assessment1_SRS_FINAL.pdf | No
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | Whole group (Wisani, Gary, Kea, Khumo, Denny) |  |  | Completed | 100 | Microsoft Project schedule finalised as TheZealotsSchedule.mpp, covering Phase 1 tasks from 17 August to 3 September with resources assigned across the group, including the consultation with Ms Mbele and GitHub setup as tracked tasks. | No
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | Kea (Keamogetse Ogone Kgosi) |  |  | Completed | 100 | Repo live at github.com/BlackZ3ro/Spanner-Riese-Auto-Clinic; folder structure finalised and pushed 31 Aug; README content pushed covering the project, tech stack, scope and team. | No
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | Gary |  |  | Completed | 100 | Supabase project created and connected to the mobile app with a working data sync, confirmed live 31 Aug. | No
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | Wisani |  |  | Completed | 100 | Progress tracker, roster and Phase Summary maintained across multiple revisions; individual contribution entries recorded for all five members and confirmed correct. | No
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | Wisani |  |  | Completed | 100 | Full group reflection covering the whole phase compiled into the final document. | No
U3-01 | Unit 3 / Phase 2 | Activity 3.1 | Draft the system architecture diagram | Wisani | 2026-09-19 | 2026-09-19 | Completed | 100 | project-docs/phase-2/system-architecture.md (Mermaid diagram grounded in the live Flutter/ASP.NET/Supabase codebase) | No
U3-02 | Unit 3 / Phase 2 | Activity 3.1 | Redraw the architecture diagram in a proper diagramming tool with a working share link | Ofentse Rammutla |  | 2026-09-21 | Completed | 100 | architecture.drawio (draw.io page 1); Lucid diagram shared by Ofentse 2 Oct | No |  | Ofentse took the architecture and UML work with Breyton on 19 Sept and shared his Lucid diagram on 2 Oct. The final architecture figure is the draw.io version.
U3-03 | Unit 3 / Phase 2 | Activity 3.2 | Draft the use case diagram (actors + use cases) | Wisani | 2026-09-19 | 2026-09-19 | Completed | 100 | project-docs/phase-2/uml-and-erd.md Part 1 | No
U3-04 | Unit 3 / Phase 2 | Activity 3.2 | Redraw the use case diagram and the sequence diagrams to the 23 Sept reference versions, with editable share links | Ofentse Rammutla and Breyton Rossouw, working together | 2026-09-21 | 2026-09-26 | Completed | 100 | Lucid (published, no account needed): https://lucid.app/lucidchart/fb4ebb76-2892-4f1a-888f-067c37aca98d/view and https://lucid.app/lucidchart/285c1247-0f85-4e60-879c-90f48a0c91f6/view | No |  | Both Lucid documents published 11 Oct so anyone can open them without an account; checked in a signed-out browser.
U3-05 | Unit 3 / Phase 2 | Activity 3.2 | Reference sequence diagrams: book in a vehicle (Flutter + web), admin finalize, admin delete, admin reopen | Wisani (reference), Gary (verify) | 2026-09-19 | 2026-09-23 | Completed | 100 | project-docs/phase-2/diagrams/*.png and diagrams/editable/*.drawio | No |  | Checked against the web code and the mobile code on main. Students redraw their own versions (U3-04).
U3-06 | Unit 3 / Phase 2 | Activity 3.2 | Sequence diagram - ASP.NET (finalize booking) | Wisani | 2026-09-19 | 2026-09-19 | Completed | 100 | project-docs/phase-2/uml-and-erd.md Part 2, Diagram 2 | No
U3-07 | Unit 3 / Phase 2 | Activity 3.2 | Entity Relationship Diagram from the live Supabase schema (draft) | Wisani | 2026-09-19 | 2026-09-19 | Completed | 100 | project-docs/phase-2/uml-and-erd.md Part 3, drawn directly from web/Models/*.cs and supabase/migrations/ | No
U3-08 | Unit 3 / Phase 2 | Activity 3.2 | Redraw the ERD in a proper tool with a working share link, and sanity-check it against mobile's actual columns | Gary |  | 2026-09-23 | Completed | 100 | project-docs/phase-2/diagrams/editable/erd.drawio (draw.io page 8); SRS Fig. 8 | No |  | ERD redrawn in draw.io (Wisani) and checked against the mobile tables on 30 Sept (booking_labor, profiles, booking_push_tokens added).
U3-09 | Unit 3 / Phase 2 | Activity 3.2 | (merged into U3-08 2026-09-20) |  |  |  | Completed | 100 |  | No |  | Merged into U3-08.
U3-10 | Unit 3 / Phase 2 | Activity 3.3 | Flutter interface wireframes (from the real, already-built screens) | Gary | 2026-09-20 | 2026-09-25 | Completed | 100 | project-docs/phase-2/wireframes/flutter-wireframes-gary.png; project-docs/phase-2/designs/gary-obsidian (Riese Auto Clinic Mockups.canvas); draw.io page 12 | No |  | Gary sent the Obsidian Canvas with the mockups and notes on 13 Oct; it is the editable source.
U3-11 | Unit 3 / Phase 2 | Activity 3.3 | ASP.NET interface wireframes (from the real, already-built screens) | Kea (Keamogetse Ogone Kgosi); screens captured by Wisani | 2026-09-20 | 2026-09-25 | Completed | 100 | project-docs/phase-2/designs/kea-web-wireframe (Kea, 25 Sept); SRS Fig. 10 and 10c | No |  | Kea shared his ASP.NET wireframe flow on 25 Sept (SRS Fig. 10c). Wisani captured the screens of the built app on 20 Sept (Fig. 10).
U3-12 | Unit 3 / Phase 2 | Activity 3.3 | Navigation flow diagram | Kea (Keamogetse Ogone Kgosi) |  | 2026-09-25 | Completed | 100 | project-docs/phase-2/diagrams/navigation-flow.png + editable/navigation-flow.drawio | No |  | Produced by Wisani on 7 Oct (drawn from the real routes in both apps) because the task was overdue; assigned owner was Kea. Recorded for individual-contribution accuracy.
U3-13 | Unit 3 / Phase 2 | Activity 3.3 | Design-alignment table (requirement -> use case -> sequence -> ERD -> interface) | Denny (Mathye MD) |  | 2026-09-27 | Completed | 100 | SRS v2.2 section 6.1 | No |  | Finished in SRS 6.1 by Wisani from the final designs; Denny, the assigned owner, produced the web designs instead (U3-30).
U3-14 | Unit 3 / Phase 2 | Activity 3.3 | Reconfirm requirements directly with Michael Riese before the design baseline is finalised (the group's own stated Phase 1 priority for this phase) | Denny (Mathye MD) |  | 2026-10-11 | Completed | 100 | SRS v2.2 4.2 (Change 7) and 4.4 (R-14 closed) | No |  | Michael Riese confirmed Change 7 (customer tracking by reference code, five phases, no time estimates). Confirmation reported to the group on 11 Oct 2026.
U3-15 | Unit 3 / Phase 2 |  | Merge all Phase 2 content into the existing SRS as one new section (no separate document, per the official brief) | Wisani | 2026-09-30 | 2026-09-30 | Completed | 100 | project-docs/Group Y - SRS v2.2 (Phase 2 - System Architecture and Design).pdf | No |  | v2.2 final (14 Oct): Gary's Obsidian mockups (Fig. 9a), Denny's Figma designs (Fig. 10a), draw.io screens, Khumo's Microsoft Project screenshots (Fig. 16) and the full Gantt (Fig. 17).
U3-16 | Unit 3 / Phase 2 |  | Apply Ms Mbele's consultation feedback - restructure use case diagram | Wisani | 2026-09-22 | 2026-09-22 | Completed | 100 | project-docs/phase-2/uml-and-erd.md Part 1, restructured; see "Consultation outcomes" table mapping each note to what changed | No |  | Consultation held 22 Sept, Lab 226 (BHP lecture halls were closed)
U3-17 | Unit 3 / Phase 2 |  | Update the Microsoft Project schedule with Unit 3 tasks + screenshot into the SRS | Moremi KE (Khumo) | 2026-09-20 | 2026-10-03 | Completed | 100 | TheZealotsSchedule.mpp (Khumo); Microsoft Project screenshots 13 Oct (SRS Fig. 16); TheZealotsSchedule (Phase 2 update 11 Oct).xml (SRS Fig. 17) | No |  | Shows the work completed for Phase 2. Phase 3 tasks will be added when Phase 3 opens.
U3-21 | Unit 3 / Phase 2 |  | Customer repair-status lookup by reference code, no login - confirmed at the 22 Sept consultation | Gary van Wyk | 2026-09-24 | 2026-09-23 | Completed | 100 | mobile/lib/features/customer (pushed 28 Sept); schema recorded in supabase/migrations/0006 | No |  | Built on mobile with a dedicated random reference_code and push notifications on phase changes. Delivered 5 days after the group target. No web page (not required).
U3-22 | Unit 3 / Phase 2 |  | Mobile login validated by Supabase Auth, role from a profiles table | Gary van Wyk | 2026-09-24 | 2026-10-01 | Completed | 100 | mobile/lib/features/auth (pushed 28 Sept) | No |  | Role picker replaced; admin-only Finalize/Delete/Reopen on mobile.
U3-23 | Unit 3 / Phase 2 |  | Apply the agreed permissions in web and mobile - only Admin can finalize, delete, reopen and remove parts/labour; both roles can restock | Wisani (web, mobile removals), Gary (mobile gates) | 2026-09-24 | 2026-10-01 | In Progress | 95 | Commits 209fd0b, 0783f04; migration 0007 | No |  | Done in code on both apps; 0007 confirmed applied live 7 Oct (delete refused for anonymous caller). Mobile part/labour removal gate awaits Gary building the app. Carried into Phase 3.
U3-24 | Unit 3 / Phase 2 |  | Revoke the Firebase service-account key that was committed to the repo, and issue a new one | Gary van Wyk | 2026-09-28 | 2026-09-29 | Not Started | 0 |  | No |  | File removed from the repo in 0783f04 and gitignored; still in git history, so the key itself must be revoked in Google Cloud. Carried into Phase 3.
U3-25 | Unit 3 / Phase 2 |  | Run migration 0007; check the reconstructed 0006 against the live schema (supabase db pull) | Gary van Wyk | 2026-09-28 | 2026-10-01 | In Progress | 50 | supabase/migrations/0006, 0007 | No |  | 0007 confirmed applied live on 7 Oct (anonymous delete refused). Still to do: supabase db pull to check the reconstructed 0006. Carried into Phase 3.
U3-26 | Unit 3 / Phase 2 | Activity 3.3 | Customer tracking page on the web (/Track), courier style, no login (FR-14) | Wisani | 2026-10-07 | 2026-10-07 | Completed | 100 | web/Pages/Track (commits d7be9bf, b6d1bb8); SRS Fig. 12 | No |  | Tested against the live database: empty, not-found and invalid-code states. Same phase labels as mobile and the push notifications.
U3-27 | Unit 3 / Phase 2 | Activity 3.3 | Mobile customer tracking screen redesign + non-blocking notification setup (proposal) | Wisani (for Gary to review) | 2026-10-07 | 2026-10-10 | In Progress | 80 | Local branch proposal/mobile-customer-tracking; mobile-customer-tracking.patch; SRS Fig. 11 | No |  | flutter analyze: 0 errors. Not pushed, by decision: Gary reviews and applies. Fixes a bug where a notification failure hid the status from a customer with a valid code. Carried into Phase 3.
U3-28 | Unit 3 / Phase 2 |  | Security: lock staff database functions to signed-in users (migration 0008) | Gary van Wyk | 2026-10-07 | 2026-10-09 | Not Started | 0 | supabase/migrations/0008_lock_staff_functions_to_signed_in_users.sql | No |  | Found 7 Oct: update_booking_phase ran for an anonymous caller with the public app key. Logged as risk R-17. 11 Oct: also run 0009 first (see U3-31), then re-run 0004 and 0008. Carried into Phase 3.
U3-29 | Unit 3 / Phase 2 | Activity 3.3 | Web phase selector on booking details (both roles, FR-15) | Wisani | 2026-10-07 | 2026-10-07 | Completed | 100 | web/Pages/Bookings/Details (commit 557be62) | No |  | Build clean; behind the staff login, so it needs a logged-in check by the group.
U3-30 | Unit 3 / Phase 2 | Activity 3.3 | ASP.NET interface designs in Figma (clickable prototype) and HTML prototype: sign-in, Today, bookings, book-in, stock, categories/suppliers, phase progress, customer tracking | Mathye MD (Denny) | 2026-10-07 | 2026-10-13 | Completed | 100 | https://www.figma.com/proto/yoiClYQl9oJNOD2pCRRplW/riese-auto-clinic-final-design?node-id=22-2240&t=xsFRVUIDXuvZZXlL-1&scaling=min-zoom&content-scaling=fixed&page-id=0%3A1 ; project-docs/phase-2/designs/denny-figma; draw.io page 13; SRS Fig. 10a | No |  | Final version in the client's green and gold with the logo. The built web app follows this layout; phase names and SMS step not adopted (FR-15/FR-16).
U3-31 | Unit 3 / Phase 2 |  | Fix "add part" on the live system (42804: old text version of add_booking_part) | Wisani (workaround) / Gary (migration 0009) | 2026-10-07 | 2026-10-12 | In Progress | 60 | supabase/migrations/0009_...sql; web workaround commit ffbd3ce | No |  | Web now adds parts without the broken function (stock decrement only if unchanged, undo on failure). Real fix: Gary runs 0009, 0004, 0008. Carried into Phase 3.
U3-32 | Unit 3 / Phase 2 | Activity 3.3 | Apply the client's colours (gold, green, orange) to the web app using Denny's layout | Wisani | 2026-10-11 | 2026-10-11 | Completed | 100 | web/wwwroot/css/site.css, Pages/Shared/_Layout.cshtml (commit ffbd3ce); SRS 5.6.0 | No |  | Client asked for gold and green, or gold, green and orange.
U3-33 | Unit 3 / Phase 2 | Activity 3.3 | Flutter high-fidelity mockups in Obsidian Canvas (vehicle status, role choice, home, bookings list, booking details) with notes, palette and navigation | Gary van Wyk | 2026-10-11 | 2026-10-13 | Completed | 100 | Riese_Auto_Clinic_App_Mockups.pdf (11 Oct); project-docs/phase-2/designs/gary-obsidian (Riese Auto Clinic Mockups.canvas); draw.io page 12; SRS Fig. 9a | No |  | Dark theme in gold, green and orange. Gary's notes mark which parts are built and which are design ideas.
U3-34 | Unit 3 / Phase 2 | Activity 3.3 | Interface designs redrawn in draw.io (Flutter and ASP.NET screens) and every design combined in one draw.io file with a public link | Wisani | 2026-10-11 | 2026-10-13 | Completed | 100 | project-docs/phase-2/diagrams/editable/spanner-all-designs.drawio (11 pages); https://app.diagrams.net/#Uhttps%3A%2F%2Fraw.githubusercontent.com%2FBlackZ3ro%2FSpanner-Riese-Auto-Clinic%2Frefs%2Fheads%2Fphase2%2Fdesign-docs%2Fproject-docs%2Fphase-2%2Fdiagrams%2Feditable%2Fspanner-all-designs.drawio | No |  | Opens in a browser with no account. Pages: architecture, use case, 5 sequence diagrams, ERD, navigation flow, Flutter screens, ASP.NET screens.
U3-35 | Unit 3 / Phase 2 |  | Make the GitHub repository public so lecturers can open it and the design links | Group (repo owner) | 2026-10-13 | 2026-10-13 | Completed | 100 | https://github.com/BlackZ3ro/Spanner-Riese-Auto-Clinic | No |  | Checked 13 Oct: repo and design files open without signing in. The Firebase key in the old history must stay revoked (U3-24).
U3-36 | Unit 3 / Phase 2 | Activity 3.3 | Riese Auto Clinic logo on the web app and in the draw.io screens | Wisani | 2026-10-11 | 2026-10-11 | Completed | 100 | web/wwwroot/img/riese-logo.png (commit 5d8f8c8) | No |  | Gold, green and orange logo matching the client's colours.
U3-37 | Unit 3 / Phase 2 |  | Merge the Phase 2 branch (pull request #15) into main so the repo front page shows the current work | Group | 2026-10-13 | 2026-10-14 | Completed | 100 | https://github.com/BlackZ3ro/Spanner-Riese-Auto-Clinic/pull/15 | No |  | Merged 14 Oct: the repo front page now has the web app, all designs, the SRS and the schedule.
U3-18 | Unit 3 / Phase 2 |  | Final top-up of the Progress Checker (Task Progress, Individual Contributions, Stakeholder Engagement, Challenges, Phase 2 Group Reflection) | Wisani | 2026-09-19 | 2026-10-08 | Completed | 100 | This workbook, continued from Group Y - ITC327W Progress Checker.xlsx (Phase 1 submission) | No |  | Final (14 Oct): Phase 2 summary, group reflection and every member's contribution recorded.
U3-19 | Unit 3 / Phase 2 |  | Presentation and defence rehearsal - every member able to explain the whole design | Whole group | 2026-10-13 | 2026-10-16 | Completed | 100 | Run sheet (link by link, no slides) + one notes PDF per member, sent to every member 13 Oct | No |  | Presented Fri 16 Oct 2026 to Ms Mbele and Mr G, from the real links. Feedback recorded as U3-38 to U3-47 and on the Stakeholder Engagement sheet.
U3-38 | Unit 3 / Phase 2 |  | Phase 2 submission on eThuto (due Tue 13 Oct 2026, 23:59) | Wisani (submission); whole group | 2026-10-13 | 2026-10-13 | Completed | 100 | eThuto submission (14 Oct); Ms Mbele's announcement "Final Opportunity to Submit Correct Documents" (14 Oct); TheZealotsSchedule (Phase 2 update 16 Oct).xml, task 40 | No | Ms Mbele (16 Oct presentation): the submission must be captured in the tracker and Microsoft Project. | SUBMITTED LATE by one day: the upload was missed on 13 Oct. Ms Mbele reopened the submission on 14 Oct and the group submitted that day. In Microsoft Project the task has a 13 Oct 23:59 deadline, so it shows as finishing after its deadline.
U3-39 | Unit 3 / Phase 2 | Activity 3.2 | Presentation feedback: redraw the ERD signs and lines, relabel the customers line, show which staff member records a booking | Wisani; Gary (run migration 0010) | 2026-10-16 | 2026-10-16 | Completed | 100 | project-docs/phase-2/diagrams/erd.png + editable/erd.drawio (draw.io page 8); supabase/migrations/0010_bookings_created_by.sql | No | Ms Mbele (16 Oct presentation): fix the ERD signs and lines; "customer books in" reads as if the customer uses the system; where is the mechanic? | Crow's-foot symbols at both ends, every line from PK row to FK row, legend; customers line now "has"; new bookings.created_by (staff who booked the car in). The design is done; Gary still has to run 0010 on the live database.
U3-40 | Unit 3 / Phase 2 | Activity 3.2 | Presentation feedback: customer use cases with the Supabase check and updates; every use case mapped to code, table and user input | Wisani | 2026-10-16 | 2026-10-16 | Completed | 100 | project-docs/phase-2/diagrams/usecase-restructured.png + editable/usecase.drawio (draw.io page 2); project-docs/phase-2/use-case-traceability.md | No | Mr G (16 Oct presentation): the customer use case should include the Supabase check and updates; a good use case has code, a database table and user input behind it. | Track repair status includes Check reference code in Supabase and View phase, parts and labour; "code not found" extends it; push updates; Message customer on WhatsApp.
U3-41 | Unit 3 / Phase 2 | Activity 3.2 | Presentation feedback: communication with the customer in the sequence diagrams | Wisani | 2026-10-16 | 2026-10-16 | Completed | 100 | project-docs/phase-2/diagrams/seq-1, seq-1b, seq-2 and new seq-5-customer-updates (draw.io pages 3, 4, 5, 14) | No | Mr G (16 Oct presentation): include the communication with the client in the sequence: open the app, choose customer, enter the code, see the status. | Book-in sequences end with the reference code sent on WhatsApp; finalize shows the push and a WhatsApp thank-you; new customer sequence (app, code, Supabase check, push and WhatsApp updates).
U3-42 | Unit 3 / Phase 2 | Activity 3.3 | Send the reference code on WhatsApp from the web booking page (bonus feature asked for by Mr G) | Wisani | 2026-10-16 | 2026-10-16 | Completed | 100 | web/Services/CustomerWhatsApp.cs; web/Pages/Bookings/Details; web/CLAUDE.md "Send on WhatsApp" | No | Mr G (16 Oct presentation): a little button that sends the code on WhatsApp; show it at the final presentation. | Free WhatsApp click-to-chat link (no paid API, zero budget kept): code at book-in, status updates, thank-you when closed. Build: 0 warnings, 0 errors; 24 checks pass. Still needs a click-through with a staff login.
U3-43 | Unit 3 / Phase 2 | Activity 3.3 | Send on WhatsApp button in the Flutter app (same link as the web app) | Gary van Wyk | 2026-10-19 | 2026-10-21 | Not Started | 0 | mobile/lib/features/bookings/presentation/booking_detail_screen.dart (to change) | No |  | Carried into Phase 3 if not done before the final presentation.
U3-44 | Unit 3 / Phase 2 |  | Get Riese Auto-Clinic onto Google Search and Maps (Google Business Profile) | Gary van Wyk with Michael Riese (owner); guide by Wisani | 2026-10-16 | 2026-10-23 | In Progress | 20 | project-docs/phase-2/google-business-profile.md | No | Mr G (16 Oct presentation): Riese did not come up when he searched Google; get it onto the Google results page. | Guide written. Michael has to create and verify the free profile himself; Google's review takes up to 5 business days.
U3-45 | Unit 3 / Phase 2 |  | Run migration 0010 (bookings.created_by) on the live database | Gary van Wyk | 2026-10-19 | 2026-10-19 | Not Started | 0 | supabase/migrations/0010_bookings_created_by.sql | No |  | No app change needed: the column defaults to the signed-in staff member.
U3-46 | Unit 3 / Phase 2 |  | Correct the Microsoft Project schedule and send it with this tracker to Ms Mbele (late submission) | Moremi KE (Khumo), Wisani | 2026-10-16 | 2026-10-19 | In Progress | 50 | project-docs/phase-2/schedule/TheZealotsSchedule (Phase 2 update 16 Oct).xml and gantt-16-Oct.png; this workbook | No | Ms Mbele (16 Oct presentation): the schedule showed the presentation on 23 Oct (in the future) and did not show the submission. | Presentation was linked to the 21 and 22 Oct meetings, which pushed it to 23 Oct; now 16 Oct. Submission task added with its deadline; every finished task at 100%.
U3-47 | Unit 3 / Phase 2 |  | SRS v2.3: new figures (ERD, use case, sequences, architecture) and Changes 12-13 in the change log | Wisani, Denny (Mathye MD) | 2026-10-19 | 2026-10-20 | Not Started | 0 | project-docs/phase-2/CHANGELOG.md (16 Oct entry) | No

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
Wisani Nkuna | 222010787 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report, individual contribution record and Unit 1 group reflection (U1-10, U1-11); coordinate group tracking and apply mentor feedback to the SRS | Maintained the Task Progress tracker across multiple revisions; compiled the final consolidated SRS, Feasibility Study and Risk Register; documented the group's decision to exclude customer facing job tracking from scope; drafted individual contribution entries; coordinated communication; emailed the module mentor requesting a consultation; compiled the submission bundle. | 2026-09-04 | 5-6 hours | Progress tracker; final SRS PDF; group chat thread; email to Ms Mbele; confirmed by the whole group, 4 September 2026 | Yes
Gary van Wyk | 222048911 | Unit 1 / Phase 1 | Activity 1.1-1.3 | Stakeholder engagement & requirements lead (U1-01 to U1-05); mobile app development; ASP.NET web application; Supabase setup (U1-09) | Identified and confirmed the stakeholder; documented the current process and problem statement; drafted the project aim, objectives and scope; wrote and conducted the stakeholder interview; built a working mobile app demo; created and connected the Supabase project; built a Wikimedia-based vehicle reference image lookup. | 2026-09-04 | 10-12 hours | Stakeholder interview transcript; group Google doc; mobile app demo video; Supabase dashboard; confirmed by the whole group, 4 September 2026 | Yes
Keamogetse Ogone Kgosi (Kea) | 222003092 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository (U1-08) | Set up the GitHub repository; added group members as collaborators; redesigned and pushed the finalised repo folder structure; attended the academic consultation with Ms Mbele alongside Khumo and wrote up detailed notes for the group. | 2026-09-02 | 4-5 hours | https://github.com/BlackZ3ro/Spanner-Riese-Auto-Clinic; consultation notes shared in group chat; confirmed by the whole group, 4 September 2026 | Yes
Moremi KE (Khumo) | 222062729 | Unit 1 / Phase 1 | Activity 1.1-1.3 (support) | Coordinate the Microsoft Project schedule work across the group (U1-07); attend the academic consultation with Ms Mbele | Attended the academic consultation with Ms Mbele alongside Kea and actively contributed; led the push to get the Microsoft Project schedule finished and distributed it to the group. | 2026-09-02 | 2-3 hours (ongoing) | Consultation notes shared in group chat; Microsoft Project distribution coordinated in group chat; confirmed by the whole group, 4 September 2026 | Yes
Mathye MD (Denny) | 221014861 | Unit 1 / Phase 1 | Activity 1.3 | Support the Microsoft Project schedule (U1-07, shared across the whole group) and support the Redefined Project Scope | Contributed content (definitions, voice notes, initial draft of Project Aim, Objectives and Scope) that fed into the SRS; helped with the Microsoft Project schedule; set up a Windows VM to run Microsoft Project; emailed and followed up in person with Ms Mbele, helping secure the consultation. | 2026-09-02 | 3 hours (ongoing) | Group chat messages and voice notes; Outlook email to Ms Mbele; Windows VM used to run TheZealotsSchedule.mpp; confirmed by the whole group, 4 September 2026 | Yes
Wisani Nkuna | 222010787 | Unit 3 / Phase 2 | Activity 3.1-3.3 | ERD draft, ASP.NET sequence diagram, architecture diagram draft, SRS merge, overall Phase 2 coordination and tracker update; reviewer on the ERD redraw, navigation flow and design-alignment table | Drafted the architecture, use case, sequence diagrams and ERD from the live system; built the ASP.NET web app (milestones M0-M8), the customer tracking page and the phase selector; redesigned the web app in the client's colours with the logo; merged the SRS (v2.0 to v2.2); kept the progress tracker; ran end-to-end tests on the live system; produced the navigation flow and ASP.NET wireframes when they were overdue; moved every design into one draw.io file. | 2026-10-14 | (ongoing) | GitHub commits on phase2/design-docs (merged to main 14 Oct); SRS v2.2; this tracker | Yes | 2026-10-14 | Phase 2 in progress - not yet group-verified
Gary van Wyk | 222048911 | Unit 3 / Phase 2 | Activity 3.2-3.3 | Sign off the Flutter sequence diagram against real mobile code; redraw the ERD in a proper tool with a share link and sanity-check it against mobile's columns; produce Flutter interface wireframes | Built the Flutter app (login with roles, bookings, stock, labour, invoices, phases), the reference-code lookup and push notifications, and the Supabase project; drew the Flutter wireframe flow; designed the high-fidelity Flutter mockups in Obsidian Canvas with notes on each screen (13 Oct). | 2026-10-13 | (ongoing) | project-docs/phase-2/designs/gary-obsidian (Riese Auto Clinic Mockups.canvas); draw.io page 12; app-release.apk (7 Oct); SRS Fig. 9 and 9a | Yes | 2026-10-14 | PNG export shared 2026-09-20 - still needs the editable .canvas source + link
Keamogetse Ogone Kgosi (Kea) | 222003092 | Unit 3 / Phase 2 | Activity 3.3 | Produce ASP.NET interface wireframes from the real, already-built web screens; produce the navigation flow diagram | Drew the ASP.NET wireframe flow of the staff web pages (start screen, sign-in, dashboard, bookings, booking details, stock, invoice) and shared it with the group on 25 Sept. Owns the group's GitHub repository (BlackZ3ro), which is public for the lecturers. | 2026-09-25 |  | project-docs/phase-2/designs/kea-web-wireframe; group chat 25 Sept; SRS Fig. 10c | Yes | 2026-10-14
Moremi KE (Khumo) | 222062729 | Unit 3 / Phase 2 | Activity 3.3 | Update the Microsoft Project schedule with Unit 3 tasks and produce the screenshot for the SRS | Built the Phase 1 and Unit 3 schedule in Microsoft Project: 41 tasks with owners, finish-to-start dependencies and milestones (TheZealotsSchedule.mpp, shared 8 Oct). Asked the group for help with the development tasks. | 2026-10-08 |  | TheZealotsSchedule.mpp (group chat 8 Oct); SRS 6.3 | Yes | 2026-10-14 | Final step: open the 11 Oct .xml update in MS Project, save as .mpp, screenshot.
Mathye MD (Denny) | 221014861 | Unit 3 / Phase 2 | Activity 3.3 | Reconfirm requirements directly with Michael Riese before the design baseline is finalised (sole owner); produce the design-alignment table | Designed the ASP.NET web interface in Figma (clickable prototype) and as an HTML prototype: sign-in, Today with stat cards, bookings, book-in, stock, categories and suppliers, phase progress and customer tracking; final version in the client's green and gold with the logo. Reconfirmed Change 7 with Michael Riese. | 2026-10-13 |  | https://www.figma.com/proto/yoiClYQl9oJNOD2pCRRplW/riese-auto-clinic-final-design?node-id=22-2240&t=xsFRVUIDXuvZZXlL-1&scaling=min-zoom&content-scaling=fixed&page-id=0%3A1 ; project-docs/phase-2/designs/denny-figma; draw.io page 13; SRS Fig. 10a | Yes | 2026-10-14 | Layout used for the built web app. Still open: prototype source/link; requirements reconfirmation (Change 7).
Ofentse Rammutla | 223056856 | Unit 3 / Phase 2 | Activity 3.1-3.2 | Redraw the system architecture diagram in a proper tool with a share link; paired with Breyton on the use case + sequence diagrams | Worked with Breyton on the UML: took on the use case and sequence diagrams and helped with the architecture diagram (agreed 19 Sept); shared his Lucidchart diagram with the group on 2 Oct; attended the group meetings on campus. | 2026-10-02 |  | Lucid diagram shared 2 Oct (https://lucid.app/lucidchart/3ac1210c-10a9-473b-990f-f0e9883798a1, needs publishing); group chat 19 Sept and 2 Oct | Yes | 2026-10-14
Breyton Rossouw | 222069744 | Unit 3 / Phase 2 | Activity 3.2 | Paired with Ofentse on the use case diagram and both sequence diagrams, with share links | Drew the use case diagram and the sequence diagrams in Lucidchart and published them so they open without an account. | 2026-10-11 |  | https://lucid.app/lucidchart/fb4ebb76-2892-4f1a-888f-067c37aca98d/view ; https://lucid.app/lucidchart/285c1247-0f85-4e60-879c-90f48a0c91f6/view | Yes | 2026-10-14

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026-08-19 | Unit 1 / Phase 1 | Interview | Gather requirements for stock/parts tracking, job/labour tracking and invoicing (Activity 1.2) | Gary van Wyk | Michael Riese - Owner/Head Mechanic | Wants a combined mobile+web system for shared stock visibility, parts sourcing/cost tracking, per-job labour logging by mechanic, and automatic invoice generation showing labour + parts cost. | Confirmed requirements now reflected in SRS Sections 1.6-1.11. | 5-question interview transcript (see SRS Section 1.6)
2026-09-02 | Unit 1 / Phase 1 | Academic Consultation | Review the compiled SRS, Feasibility Study and Risk Register ahead of submission | Keamogetse Ogone Kgosi (Kea) and Moremi KE (Khumo) | Ms Mbele, Module Mentor (ITC327W) | Document should be fully justified in Arial with 1.15 line spacing and a dedicated cover page; directly/indirectly affected users needed clearer separation; a customer-facing real-time job tracking feature was suggested as a possible enhancement. | Applied all formatting changes; documented the decision to exclude customer-facing tracking from scope. | Consultation notes from Kea; updated SRS: Spanner_ITC327W_Assessment1_SRS_FINAL.pdf
2026-09-22, 12:00 | Unit 3 / Phase 2 | Academic Consultation | Phase 2 readiness check - architecture, UML, ERD, interface designs (Group Y's slot) | All | Ms Mbele, Module Mentor (ITC327W) | Use case diagram had too many top-level ovals and needed restructuring into base use cases with extend points; View dashboard should be an extension of Login, not standalone; add filtering between open/closed jobs; label authentication directly on the Admin-only extension points. Separately, confirmed a new requirement: a customer-facing repair-status lookup by reference code, no login required. | Use case diagram restructured same day (see uml-and-erd.md). New feature logged as U3-21, not yet assigned an owner, group target 23 Sept. | project-docs/phase-2/consultation-prep-2026-09-22.md; project-docs/phase-2/uml-and-erd.md
2026-10-11 (reported) | Unit 3 / Phase 2 | Requirements reconfirmation | Confirm Change 7: customer repair-status tracking by reference code (FR-14) with phase notifications (FR-15, FR-16), partially reversing Change 5 | Group (reported to Wisani) | Michael Riese - Owner/Head Mechanic | Michael Riese confirmed Change 7. The no-estimate, five-phase design answers his Phase 1 concerns | Close R-14; keep Change 7 in the design baseline | Group chat confirmation, 11 Oct 2026
2026-10-16, 12:00 | Unit 3 / Phase 2 | Presentation (Phase 2 defence) | Present the Phase 2 design: architecture, use case and sequence diagrams, ERD, interface designs, schedule and this tracker | Group Y members (see recording) | Ms Mbele, Module Mentor (ITC327W); Mr G, lecturer | Mr G: a good use case has code, a table and user input behind it; show the Supabase check, updates and the communication with the customer; bonus: send the reference code on WhatsApp; Riese does not come up on Google. Ms Mbele: ERD signs and lines unclear, the customers line reads as if the customer uses the system, and the staff are not visible; the schedule showed the presentation on 23 Oct and did not capture the late submission. Positive: everyone knows the whole system, and the design is simple. | U3-38 to U3-47 (Task Progress). Feedback applied to the designs and web app on 16 Oct; schedule and tracker to be sent to Ms Mbele. | Recording (4).m4a and its transcript (group OneDrive); project-docs/phase-2/CHANGELOG.md, 16 Oct entry

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
2026-08-31 | Unit 1 / Phase 1 | Denny cannot run Microsoft Project natively on his PC | Delays completion of the initial schedule (U1-07) | Set up a Windows VM and install MS Project there; schedule finalised and submitted as TheZealotsSchedule.mpp. | Denny (Mathye MD) | Before Friday submission | Resolved
2026-08-31 | Unit 1 / Phase 1 | Uncertainty over the exact submission date | Risk of compiling/submitting to the wrong deadline | Confirmed Friday, 4 Sept as the deadline with the group. | Whole group | Friday, 4 September 2026 | Resolved
2026-09-02 | Unit 1 / Phase 1 | Academic consultation raised formatting requirements and a content suggestion that needed evaluating against the stakeholder's own operational preference | Risk of the SRS not reflecting mentor feedback, or of building a feature the stakeholder doesn't want | Applied all formatting feedback; evaluated the suggestion against direct stakeholder input and documented the decision to exclude it. | Wisani (compiled); Gary (stakeholder input) | Before Friday submission | Resolved
2026-09-02 | Unit 1 / Phase 1 | Khumo's individual contribution was not yet logged in the tracker | The assessment requires each student's work to be self-reported with evidence | Attended the academic consultation with Kea and is coordinating the Microsoft Project schedule; individual contribution entry added. | Moremi KE (Khumo) | Before Friday submission | Resolved
2026-09-04 | Unit 1 / Phase 1 | Three items were still open going into submission night: the signed stakeholder letter, the GitHub README, and group confirmation of the individual contribution records | Risk of submitting with an unconfirmed stakeholder relationship, an empty repository README, or unverified individual contribution entries | Signed confirmation letter collected and added as SRS Appendix E; README pushed; individual contribution records reviewed and confirmed by the whole group. | Whole group | Friday, 4 September 2026 | Resolved
2026-09-19 | Unit 3 / Phase 2 | Two new members (Ofentse Rammutla, Breyton Rossouw) joined mid-Unit 3 with unknown skill level in UML notation | Risk of one new member (Breyton, who had volunteered to take "the UML diagrams" solo since he had no other task yet) getting stuck alone on unfamiliar work, or of the diagrams needing significant rework | Reassigned the use case diagram and both sequence diagrams from a one-each split to a joint, paired task for both new members, so they work through it together instead of solo. | Wisani (reassigned); Ofentse Rammutla and Breyton Rossouw (doing the paired work) | 2026-09-21 | In Progress
2026-09-19 | Unit 3 / Phase 2 | Web and mobile currently calculate invoice labour totals from two different places (booking_labor on mobile vs jobs.labour_hours x labour_rate on web), against the same live bookings | Risk of invoice totals disagreeing between the two apps for the same booking | Flagged in project-docs/phase-2/uml-and-erd.md and web/CLAUDE.md for a team decision; not yet fixed. Raising it directly with Ms Mbele at the 22 Sept consultation. | Whole group (decision pending) | 2026-09-25 | Open
2026-09-20 | Unit 3 / Phase 2 | Wisani was the owner on ~10 active Phase 2 items plus reviewer on most others - the same solo-overload pattern as her Phase 1 SRS/tracker/reflection load | Risk of her becoming the bottleneck for the whole phase, and of her individual contribution record looking like she did everyone's design work rather than her own | Moved the ERD redraw to Gary (merged with his existing sanity-check task), the navigation flow diagram to Kea (pairs with her ASP.NET wireframes), and the design-alignment table to Denny (matches his Phase 1 content-support role); dropped her as co-owner of the stakeholder reconfirmation. She keeps the SRS merge and tracker top-up, both direct continuations of her established Phase 1 role, plus reviewing the moved items. | Wisani (reassigned); Gary, Kea, Denny (now own the moved items) | 2026-09-20 | Resolved
2026-09-20 | Unit 3 / Phase 2 | The use case diagram assumed Reopen booking was admin-only; live testing against the real app (mechanic login) showed OnPostReopenAsync never checks IsAdmin, and View closed bookings is on the shared nav for both roles | Design docs would have misrepresented actual access control, which the Design Alignment rubric line specifically checks | Corrected the use case diagram and uml-and-erd.md - Reopen booking and View closed bookings moved from the admin-only cluster to shared Mechanic use cases. Only Finalize & close and Delete booking are genuinely admin-gated. Flagged as a team decision: should Reopen also be locked to admin for consistency? | Wisani | 2026-09-20 | Resolved (design docs corrected); open (whether to change the code)
2026-09-22 | Unit 3 / Phase 2 | Ms Mbele confirmed a new requirement at the consultation (customer repair-status lookup, no login) with a group target of 23 Sept, but no one has been assigned to build it yet | Risk of the deadline slipping with nobody actually accountable for it, and of the reference-code implementation being guessed rather than confirmed against the real schema | Logged as U3-21 in this tracker and in uml-and-erd.md's "New feature" section, including the open question for Gary (reuse invoice_number vs a new column) and the new-unauthenticated-route note in system-architecture.md. Needs the group to actually assign an owner - flagged here rather than left implicit. | Unassigned (open) | 2026-09-23 | Open - needs an owner
2026-09-23 | Unit 3 / Phase 2 | Review of the student UML and sequence diagrams against the real web and mobile code found mismatches (Flutter diagram used the wrong table, a fake Check-IsAdmin call to Supabase, no login step, Loop frames, flat use case layout) and that mobile has no real authentication | Design docs would not have matched the system, which the Design Alignment rubric line checks | Corrected reference diagrams saved in project-docs/phase-2/diagrams; permissions agreed (only Admin finalizes, deletes, reopens, removes jobs); tasks U3-22 and U3-23 added; students to redraw and share editable links | Wisani | 2026-09-23 | In progress
2026-09-28 | Unit 3 / Phase 2 | Review of Gary’s 28 Sept mobile push found a Firebase private key committed to the repo, schema changes made only in the dashboard (not in migrations), web not updating the new booking phase, and mobile deletes split across several calls | Leaked key could be misused; the ERD and repo would not show the real schema; customers could see a wrong repair phase; stock could drift from bookings | Key file removed and gitignored (Gary to revoke the key); schema recorded as migration 0006; web finalize/reopen set the phase; mobile delete uses one atomic database function with an admin check (0007) | Wisani | 2026-09-28 | In progress - key revocation and 0007 pending (Gary)
2026-09-30 | Unit 3 / Phase 2 | Full recheck found the architecture and ERD no longer matched the system after the 28 Sept mobile push (no Edge Function/Firebase, missing booking_labor, profiles, booking_push_tokens), and that push notifications reverse a Phase 1 scope exclusion | Design Alignment marks depend on the documents matching the built system; an unrecorded scope change would read as uncontrolled scope creep | Architecture and ERD updated and re-validated; scope change to be recorded in the SRS Requirements Change Log as approved at the 22 Sept consultation | Wisani | 2026-09-30 | In progress - SRS change log entry due with the SRS merge
2026-10-07 | Unit 3 / Phase 2 | Testing the live system as an anonymous user found that the phase-change function could be run without logging in (Postgres grants EXECUTE to everyone by default); the navigation flow and customer pages were overdue | Anyone with a booking id could change its phase and trigger a customer notification; missing design items would cost Design Alignment and interface marks | Migration 0008 written to revoke anonymous access (Gary to run); navigation flow, web /Track page and mobile tracking design produced and attributed to Wisani in this tracker | Wisani / Gary | 2026-10-09 | In progress - 0008 to be run
2026-10-11 | Unit 3 / Phase 2 | Adding a part failed on the live system (42804) because an old text-typed copy of add_booking_part still exists; only Gary can run SQL on the live project | Staff could not add parts to a booking from the web app | Web app adds parts directly when the function fails (safe stock check, undo on failure); migration 0009 written for Gary | Wisani / Gary | 2026-10-12 | Workaround live; 0009 to be run
2026-10-11 | Unit 3 / Phase 2 | Three different visual styles (Denny web, Gary mobile, Wisani /Track); client asked for gold and green, or gold, green and orange | Inconsistent look across the two apps and the SRS | One palette for both apps: green (brand, done), gold (highlights), orange (actions, in progress); web rebuilt on Denny's layout | Wisani / Denny / Gary | 2026-10-11 | Done on web; mobile to follow
2026-10-13 | Unit 3 / Phase 2 | Design links needed accounts (Lucid sign-in, private GitHub repo, Claude-hosted pages), so lecturers could not open them | Risk of losing the source-links marks and of a failed demo on presentation day | Lucid documents published; repo made public; all designs moved into one draw.io file that opens from GitHub with no account; presentation run from those links instead of slides | Breyton / repo owner / Wisani | 2026-10-13 | Done
2026-10-14 | Unit 3 / Phase 2 | The Phase 2 submission missed the deadline (Tue 13 Oct, 23:59): the work was finished but the upload was not done in time | Late submission that Ms Mbele has to report; risk of losing marks | Emailed Ms Mbele just after the deadline asking her to accept the work; she reopened the submission on 14 Oct and the group submitted that day (and thanked her). Recorded as U3-38 and in Microsoft Project with the 13 Oct deadline. From Phase 3: internal deadline two days early, one named person uploads. | Wisani / whole group | 2026-10-14 | Resolved - submitted late
2026-10-16 | Unit 3 / Phase 2 | Microsoft Project showed the presentation on Fri 23 Oct instead of Fri 16 Oct, and had no task for the Phase 2 submission | At the presentation the schedule did not match what happened ("in the future") | Presentation linked to the 15 Oct meeting and moved to 16 Oct; submission task added with its deadline; progress filled in; post-presentation feedback tasks added (16 Oct XML and Gantt) | Khumo / Wisani | 2026-10-19 | In progress - send to Ms Mbele
2026-10-16 | Unit 3 / Phase 2 | Lecturers could not read the ERD clearly (signs, lines, customers line) and could not see which staff member records a booking | Design marks at risk; questions at the defence | ERD redrawn with crow's-foot signs and PK-to-FK lines; customers line relabelled; bookings.created_by added (migration 0010) | Wisani / Gary | 2026-10-19 | Design done; Gary to run 0010

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 1 / Phase 1 | Initial or updated SRS completed | Yes
Reporting period | Unit 1 / Phase 1 - submitted Friday, 4 September 2026 | Progress report updated | Yes
Overall phase status | Submitted (80% achieved) | Individual contributions recorded | Yes
What was completed during this phase? | Stakeholder confirmed and interviewed; SRS, feasibility study and risk register compiled and revised; working mobile app demo built; Supabase connected and syncing; Microsoft Project schedule finalised; GitHub repository structured; individual contribution entries recorded for all five group members. | Stakeholder engagement recorded | Yes
What remains incomplete? | Nothing blocking - each member's confidential individual peer evaluation was completed separately on Blackboard per Rule 6. | Challenges and actions updated | Yes
Which contributions were particularly important? | Gary's early stakeholder access and head start on the mobile app; Kea's initiative on GitHub and the academic consultation; Khumo leading the Microsoft Project push; Denny's persistence in securing the consultation. | Group reflection completed | Yes
Were there participation concerns? | No. Khumo's contribution was initially missing from the tracker but was logged before submission. | Microsoft Project updated | Yes
What will the group improve in the next phase? | Move faster from informal conversation to documented evidence earlier in the phase, and get mentor feedback earlier rather than close to the deadline. | GitHub evidence available | Yes
Main priority for the next phase | Confirm the requirements directly with Michael Riese before starting UML, ERD and interface design in Phase 2. | Confidential peer check completed | Yes
Reporting phase | Unit 3 / Phase 2 | Initial or updated SRS completed | Yes (v2.2)
Reporting period | 19 September to 16 October 2026 | Progress report updated | Yes
Overall phase status | Complete. Submitted late: due Tue 13 October 23:59, submitted Wed 14 October after Ms Mbele reopened the submission. Presented on Fri 16 October; the feedback is being applied (U3-38 to U3-47). | Individual contributions recorded | Yes
What was completed during this phase? | System architecture, use case diagram, five sequence diagrams, ERD, navigation flow, Flutter mockups (Gary), ASP.NET designs (Denny), draw.io versions of every design in one file, design alignment table, SRS v2.2, Microsoft Project schedule and this tracker. Built and tested: the web app (M0-M8), customer tracking by reference code on web and mobile, booking phases with push notifications, and the client's colours and logo on the web app. | Stakeholder engagement recorded | Yes
What remains incomplete? | Database fixes 0008 and 0009 on the live project, the mobile app in the client's colours, and merging the mobile tracking redesign. These move to Phase 3. From the 16 Oct presentation: the WhatsApp button in the mobile app, migration 0010 on the live database, the Google Business Profile (Michael), SRS v2.3, and sending the corrected schedule and this tracker to Ms Mbele. | Challenges and actions updated | Yes
Why is it incomplete? | Only Gary can run SQL on the live database, and the client confirmed the colour scheme only in October. | Group reflection completed | Yes
Which contributions were particularly important? | Gary's mobile app and notifications; the web app and the documentation; Denny's web designs; Breyton's published Lucid diagrams; Khumo's schedule. | Microsoft Project updated | Yes
Were there participation concerns? | Two members joined on 15 September with less time. Some design tasks ran late and were picked up by other members; Task Progress records who did each one. | GitHub evidence available | Yes (public, merged to main)
What will the group improve in the next phase? | An internal deadline two days before every due date, with one named person responsible for uploading. | Confidential peer check completed | Each member separately
Main priority for the next phase | Send Ms Mbele the corrected schedule and this tracker, finish the 16 Oct feedback items, then plan Phase 3 in Microsoft Project as soon as the brief opens.

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 1 / Phase 1 | Length | Approximately 300-400 words in total.
Project title | Spanner - Workshop Booking, Stock & Invoicing System | Focus | Discuss the group's actual experience, not the activity instructions.
Most important learning from this phase | Having direct access to a real external stakeholder, Michael Riese, made it possible to ground the requirements in an actual day-to-day workflow instead of an assumed one. Taking the compiled SRS to an academic consultation with Ms Mbele added a second, equally valuable layer of feedback. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | Gary had already started scoping and building a mobile prototype before the module formally began. Kea took ownership of the GitHub repository without being asked and attended the consultation on the group's behalf. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | Getting time with Ms Mbele took real persistence - two emails went unanswered before Denny followed up in person. Denny also could not run Microsoft Project on his own PC. A genuine scope question came up over customer-facing real-time job tracking, resolved against Gary's direct stakeholder knowledge. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Gary led stakeholder engagement, the interview, the mobile app and Supabase; Kea owned GitHub and attended the consultation with Khumo; Khumo coordinated the Microsoft Project schedule; Denny supported the SRS content and secured the consultation; Wisani compiled the tracker, SRS, contribution records and this reflection.
Did all members contribute fairly? Explain. | Yes. Gary and Kea are ahead on technical/setup work but used that head start to pull the team forward. Khumo's contribution was slower to show up in the tracker but substantial once logged. Denny's persistence in chasing the consultation was just as valuable even though it was not a technical contribution.
How did the group handle disagreements or delays? | The only real point of discussion was the customer-tracking suggestion, resolved by documenting the decision and its reasoning in the SRS and flagging it to the group for confirmation.
What did the group learn from the stakeholder? | That parts and stock costing is currently tracked informally with no fixed markup rule, and that vehicle-identifying details are kept to protect the business. From Ms Mbele: a technically complete document still needs to be readable, and a suggested feature is worth evaluating seriously even when the group decides against it.
Improvement action 1 for the next phase | Get the document in front of a mentor earlier in the phase rather than close to the deadline.
Improvement action 2 for the next phase | Chase confirmations more assertively and earlier, instead of waiting for replies that may not come.
Priority for the next phase | Each member completes their confidential peer evaluation on Blackboard, then the group confirms the requirements directly with Michael Riese before starting UML, ERD and interface design in Phase 2.
Reporting phase | Unit 3 / Phase 2
Project title | Spanner - Workshop Booking, Stock & Invoicing System
Most important learning from this phase | Designing from a system that already runs keeps the design honest. Every time we checked a diagram against the real code or database we found something to fix, from a missing table in the ERD to a function that worked without logging in. A design is only useful if it matches what is built.
What went well and why? | Both apps work on one shared Supabase database. Gary built the mobile app, the reference-code lookup and push notifications; the web app reached all nine milestones; Denny's web designs gave us one layout to build on; Breyton published the Lucid diagrams so anyone can open them; and Michael Riese confirmed the customer tracking change and chose the gold, green and orange colours.
What was difficult and why? | Two members joined in the middle of the phase. Several design tasks ran late and were finished by others. Some design links needed an account to open, so we had to publish them and move every design into draw.io. Most seriously, we missed the submission deadline because everyone assumed someone else would upload.
How were tasks divided among members? | Each member owned one part (architecture, UML, ERD, Flutter design, ASP.NET design, schedule, tracker and SRS), and the person closest to each part presents it.
Did all members contribute fairly? Explain. | Contributions were uneven: some members carried more of the building and documentation, and two members had less time because they joined late. The Individual Contributions sheet records who did what, with evidence.
How did the group handle disagreements or delays? | We discussed whether customers should also track their car on the website; we kept it because the consultation asked for a customer screen. When tasks became overdue, another member completed them and the tracker records who did.
What did the group learn from the stakeholder? | Michael does not want time estimates shown to customers, because parts delays are out of his control. Five broad phases with notifications give customers peace of mind without promises he cannot keep.
Improvement action 1 for the next phase | An internal deadline two days before every due date, with one named person responsible for uploading.
Improvement action 2 for the next phase | Share and publish every design link the day it is made, and test it in a signed-out browser.
Priority for the next phase | Plan Phase 3 in Microsoft Project as soon as the brief opens, and apply the Phase 2 feedback.